## ProjectSchedule
Campus Recruitment System
[Project Based Learning] |  | Project Start: | 2021-02-01
|  | Today: | 2021-03-01
|  | Display Week: | 1 |  |  | 2021-02-01 | [6 empty] | 2021-02-08 | [6 empty] | 2021-02-15 | [6 empty] | 2021-02-22 | [6 empty] | 2021-03-01 | [6 empty] | 2021-03-08 | [6 empty] | 2021-03-15 | [6 empty] | 2021-03-22
 | time axis 2021-02-01 to 2021-03-28
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2021-02-01 to 2021-03-28
Phase 1 Review of Idea
Problem Statement and Objectives | Swaleha | 100% | 2021-01-02 | 2021-02-08 | 38
Recruiters Dashboard | Yuvraj | 100% | 2021-01-02 | 2021-02-08 | 38
Admin Dashboard | Mohammad Bilal | 100% | 2021-01-02 | 2021-02-08 | 38
Student Dashboard | Vaishnavi | 100% | 2021-01-02 | 2021-02-08 | 38
Technologies to be used | Sudarshan | 100% | 2021-01-02 | 2021-02-08
Conclusion | All members | 100% | 2021-01-02 | 2021-02-08 | 38
Phase 2 Literature Survey
Existing System | Swaleha | 100% | 2021-02-08 | 2021-02-15 | 8
Pros and Cons in Existing System | Vaishnavi | 100% | 2021-02-09 | 2021-02-16 | 8
Technical Paper Part I | Mohammad Bilal | 100% | 2021-02-10 | 2021-02-17 | 8
Technical Paper Part II | Yuvraj | 100% | 2021-02-11 | 2021-02-18 | 8
Analysis of Placements | Sudarshan | 100% | 2021-02-12 | 2021-02-19 | 8
Phase 3 Describe Features of Dashboards
Admin Dashboard | Mohammad Bilal, Yuvraj | 100% | 2021-02-15 | 2021-02-22 | 8
Recruiters Dashboard | Sudarshan, Yuvraj | 100% | 2021-02-16 | 2021-02-22 | 7
Student Dashboard | Swaleha, Vaishanvi | 100% | 2021-02-17 | 2021-02-22 | 6
Phase 4 Implementation of Login Module
Login Page for Students | Sudarshan | 0% | 2021-03-01 | 2021-03-17 | 17
Login Page for Recruiters | Mohamamd Bilal, Yuvraj | 0% | 2021-03-02 | 2021-03-18 | 17
Login Page for Admin | Swaleha, Vaishanvi | 0% | 2021-03-03 | 2021-03-19 | 17
Phase 5 Implementation of Student Dashboard
Registartion Module | Sudarshan | 0% | 2021-03-19 | 2021-04-01 | 14
Automatic CV Creation | Bilal | 0% | 2021-03-20 | 2021-04-02 | 14
Detailed Information about Companies Registered | Swaleha | 0% | 2021-03-21 | 2021-04-03
FAQs Section | Vaishnavi | 0% | 2021-03-22 | 2021-04-04 | 14
View Schedule | Sudarshan | 0% | 2021-03-23 | 2021-04-05
Notifications | Yuvraj | 0% | 2021-03-24 | 2021-04-06
Vacancy Menu for Search vacancies | Swaleha | 0% | 2021-03-25 | 2021-04-07 | 14
Authentication | Yuvraj | 0% | 2021-03-26 | 2021-04-08
Unit Testing | Yuvraj | 0% | 2021-03-27 | 2021-04-09 | 14
Phase 6 Implementation of Recruiters Dashboard
Registartion Module | Sudarshan | 0% | 2021-04-26 | 2021-04-30 | 5
Add Placement Vacancies | Bilal | 0% | 2021-04-27 | 2021-05-01 | 5
Scheduling the interview and apttitude test | Sudarshan | 0% | 2021-04-28 | 2021-05-02 | 5
Authentication | Yuvraj | 0% | 2021-04-29 | 2021-05-03 | 5
Phase 7 Implementation of Admin Dashboard
Granting Permissions | Sudarshan | 0% | 2021-05-01 | 2021-05-04 | 4
View Records | Bilal | 0% | 2021-05-02 | 2021-05-05 | 4
Analysis of Placements | Sudarshan | 0% | 2021-05-03 | 2021-05-06 | 4
Generate Report | Bilal | 0% | 2021-05-04 | 2021-05-07
Authentication | Yuvraj | 0% | 2021-05-05 | 2021-05-08
Phase 8 System Testing
Student Dashboard | Yuvraj, Vaishnavi | 0% | 2021-05-07 | 2021-05-09 | 3
Recruiters Dashboard | Swaleha, Bilal | 0% | 2021-05-08 | 2021-05-10 | 3
Admin Dashboard | Swaleha, Sudarshan | 0% | 2021-05-09 | 2021-05-11 | 3
Phase 9 Miscellaneous
Progressive Web App (PWA) | Yuvraj,Sudarshan | 0% | 2021-05-11 | 2021-05-12 | 2
Deployment | Sudarshan, Bilal | 0% | 2021-05-12 | 2021-05-13 | 2
Maintaining Documentation of Project | Swaleha, Vaishanvi | 0% | 2021-05-13 | 2021-05-14 | 2
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.